## RFP - PM Tender Tooting
STATE BANK OF INDIA (UK) LTD
RFP - PROJECT MANAGEMENT TENDER
NEW TOOTING BRANCH
|  | GENERAL STAGES | COST
1 | 1 | Following appointment - Undertake Branch measured site Survey to Tooting, review retail unit and provide a condition report | 0
| 2 | Speak to key supply chain to ascertain their status | 0
| 3 | Determine if a Structural Engineer will be required | 0
| 4 | Consult with SBI Retail Operations, Security, IT, FM, H&S and Marketing Dept | 0
| 5 | Identify Client direct supply items with lead in times | 0
| 6 | Create concept and space plan layout | 0
| 7 | Develop the detailed design producing the required drawings as listed below in section 3.5 | 0
| 8 | Undertake and oversees Building Control tender process, review tender returns, report to SBI with recommendation | 0
| 9 | Produce a Pack of information for SBI to issue to the Landlord for Landlords Approval | 0
| 10 | Draft list of potential Contractors, invite SBI to add to list | 0
| 11 | Issue Pre-Qualification Questionnaire to each contractor | 0
| 12 | Review PQQ returns and report | 0
| 13 | Pre-vet both Mechanical and Electrical specialist sub-contractors | 0
| 14 | Undertake and oversee Main Contractor Tendering process, review tender returns, report to SBI | 0
| 15 | Advise and report to SBI on recommendation, form of contract, and contractor appointment | 0
| 16 | Advise on risk factors and mitigation solutions | 0
| 17 | Manage the project from inception to final completion and full handover to SBI | 0
|  | General Stages Total | 0
ELEMENTS IN DETAIL
|  | CONCEPT DESIGN | COST
2 | 1 | Visit Tooting branch, carry out a measured site survey | 0
| 2 | Undertake space planning exercise | 0
| 3 | Meet in Harrow office to Consult with Retail Head for business operations and functionality | 0
| 4 | Create design concept for the new Consultantion Premier branch | 0
| 5 | Produce up to 3 different layout versions for SBI to review | 0
| 6 | Produce 3D Visuals of proposed branch | 0
| 7 | Review existing Design and necessary materials and specification updates | 0
| 8 | Meet with existing/ new Branch Manager and review any issues that may have arisen with the Banks principal layout, materials used, wear ability of products | 0
| 9 | Review current specifications - Update as necessary | 0
| 10 | Check that materials, colours etc are still available and suitable for application | 0
| 11 | Re-confirm furniture availability | 0
| 12 | Re-Confirm specialist manufacturing sub-contractor’s product status | 0
| 13 | Amend and Updated SBI Branch Specification document | 0
| 14 | Produce full set of Architectural and Mechanical HVAC design drawings as detailed below in Drawing requirements | 0
0
|  | Concept Design Total | 0
DETAILED DESIGN DEVELOPMENT
|  | DRAWINGS REQUIRED | COST
3 |  |  | 0
| 1 | Following the measured site survey, space planning exercise, and concept design stage; develop the detailed design ensuring drawing accuracy and scheme buildability | 0
| 2 | Produce a full set of drawings to enable a contractor to price the project at Tender stage | 0
| 3 | Amend these drawings as maybe necessary to update for Construction issue | 0
| 4 | Following the build process, compile and issue a set of "As Built" drawings to the State Bank of India for record | 0
| 5 | List of drawings – | 0
|  | 1 - Existing Building | 0
|  | 2 - Demolition | 0
|  | 3 - General Arrangement layout | 0
|  | 4 - Finishes | 0
|  | 5 - Partitions | 0
|  | 6 - Secure Partitions | 0
|  | 7 - Reflective Ceiling Plan (RCP) | 0
|  | 8 - Merchandising | 0
|  | 9 - Furniture layout | 0
|  | 10 - Fire Strategy, alarm system full scope | 0
|  | 11 - Electrical Power | 0
|  | 12 - Lighting | 0
|  | 13 – Containment | 0
|  | 14 – Mechanical HVAC | 0
|  | a) Fan Coils | 0
|  | b) A/C units | 0
|  | c) Duct work runs | 0
|  | d) Grilles | 0
|  | e) Roof & External Plant Location | 0
|  | 15 - Drainage | 0
|  | 16 - External Elevation (including shopfront) | 0
|  | 17 - Door details | 0
|  | 18 - Sprinkler existing and amended | 0
|  | 19 - External Signage | 0
|  | 20 - Plannig Approval | 0
|  | DETAILED DESIGN DEVELOPMENT & DRAWINGS TOTALS | 0
|  | LANDLORD - LTA - RULES FOR SBI OCCUPATION AND TRADE | COST
4 |  |  | 0
| 1 | Landlords Licence to Alter Approval - Incorporate drawings, specifications and Contractors scope of works and method statement into a Pack to issue to SBI for subsequent issue to the Landlord for Landlords Approval | 0
| 2 | Assist SBI with any landlord requirements | 0
|  | Landlord - LTA - Rules for SBI Occupation Totals | 0
|  | CDM 2015 REGULATIONS AND PRINCIPAL DESIGNER | COST
5 | 1 | Principal Designer under CDM regulations (Construction Design Management) - Act as SBI’s Principal Designer and produce Pre-Construction Health & Safety Plan and comply with the regulations | 0
| 2 | Vet and review contractors Construction Health & Safety Plan | 0
| 3 | Review and approval all the contractors RAMS (Risk Assessments & Method Statements) | 0
| 4 | Comply with all duties under the CDM regulations | 0
|  | CDM Regulations and Principal Designer Totals | 0
|  | PLANNING APPROVAL | COST
6 | 1 | Assume responsibility for all Planning requirements, including submission of Planning Applications incorporating necessary drawings & documents together with any negotiations / chasing to achieve Planning Approval | 0
| 2 | Assume responsibility for Advertising Consent or amendment to the existing as part of the Planning Application | 0
|  | Planning Approval Totals | 0
|  | BUILDING REGULATIONS | COST
7 | 1 | Undertake Building Control Tender process on behalf of SBI | 0
| 2 | Report on tender and advise on a recommendation | 0
| 3 | Consult with Building Control and Fire Officer to gain Building Regulations approval Certificate | 0
| 4 | Issue internal layout drawings for comment | 0
| 5 | Issue scope and specifications | 0
| 6 | Develop Fire Strategy for Building Control approval | 0
|  | Building Regulations Totals | 0
|  | DOCUMENTS REQUIRED | COST
8 | 1 | Produce updated specifications | 0
| 2 | Prepare and produce a Scope of Works document for Contractors Tender | 0
| 3 | Draft up a Pricing Schedule | 0
| 4 | Create a Commercial client cost analysis report | 0
| 5 | Site meeting Agenda | 0
| 6 | Client Project Progress report | 0
| 7 | Draft Contractor appointment letter | 0
| 8 | Obtain a copy, amend as necessary and issue a suitable JCT works contract | 0
| 9 | Project Valuation Certificate | 0
| 10 | Project sign off Certificates | 0
| 11 | Coordinate and issue all contractor tender documents | 0
| 12 | Produce Pre-Construction Health & Safety Plan | 0
|  | Documents Required Totals | 0
|  | SBI DIRECT INTERFACE | COST
9 | 1 | Arrange meetings with SBI inhouse directs, interface and agree technical details, cable routes, lead in times and programme | 0
| 2 | Security - Allow to review security quotations, comment and advise on recommendations | 0
| 3 | IT Systems Team | 0
| 4 | Facilities Management | 0
| 5 | Marketing | 0
| 6 | SBI Health & Safety | 0
| 7 | Establish full updated contact sheet | 0
|  | SBI Direct Interface Totals | 0
|  | PROJECT MANAGEMENT | COST
10 | 1 | To act on behalf of the State Bank of India in matters relating to the delivery of project design, maintain high quality Design, Health & Safety and Project delivery standards, to monitor, control each project and its appointed contractor and act as the Banks Project Manager / Clients Agent / Contract Administrator | 0
| 2 | Manage and report on all Change and Cost Control, Valuations, Commercial reporting and Sign Off's | 0
| 3 | Project – Tooting | 0
| 4 | Attend 2 No site survey meetings with each Tendering Contractor | 0
| 5 | Answer all tender queries | 0
| 6 | Prepare and submit post Tender analysis report | 0
| 7 | Attend Client bid opening meeting (Harrow office) | 0
| 8 | Arrange and attend Contractor interview at SBI Harrow office | 0
| 9 | Arrange contractor design coordination meeting (including SBI Security, IT Team, Marketing) | 0
| 10 | Liaise with contractor pre & post appointment | 0
| 11 | Draft and issue contractor appointment letter (LOI) | 0
| 12 | Arrange and attend contractors pre-start meeting | 0
| 13 | Attend Formal Weekly Site Meetings (while under construction) | 0
| 14 | Attend 2 No informal site visits to check on project status, progression and technical detail | 0
| 15 | Check and advise on Health & Safety on site | 0
| 16 | Ensure the contractors Environmental and Waste management methods are correct and aligned to the Construction H&S Plan AND LANDLORDS REQUIREMENTS | 0
| 17 | Review and approval all the contractors RAMS (Risk Assessments & Method Statements) | 0
| 18 | Prepare and issue client weekly progress report | 0
| 19 | Prepare and issue Valuation Certificates | 0
| 20 | Allow to attend a number of regular Client Head Office meetings as necessary (assume 2/3 hrs each) - Harrow office | 0
| 21 | 2 No Snag / Close Out visits to site | 0
| 22 | Prepare and issue Contract documents for Practical Completion | 0
| 23 | 2 No Final Account meetings with contractor and issue final commercial report to the client | 0
| 24 | Check the contractors issue a full O&M Manual (Operations & Maintenance Manual) on completion of each project with the appropriate Certificates | 0
| 25 | Defects Liability Period - 1 year after Practical Completion (PC), undertake a site inspection of the branch and draft the 12 months defects list (share with contractor & client) | 0
| 26 | Review and agree with contractor | 0
| 27 | Inspect defects on completion | 0
| 28 | Issue final project completion certificate | 0
|  | Project Management Totals | 0
FEE COLLECTION SUMMARY
| 1 | General Stages | 0
| 2 | Concept Design | 0
| 3 | Drawings Required | 0
| 4 | Landlord LTA | 0
| 5 | CDM Regulations and Principal Designer | 0
| 6 | Planning Approval | 0
| 7 | Building Control | 0
| 8 | Documents Required | 0
| 9 | SBI Directs Interface | 0
| 10 | Project Management | 0
|  | Tender Total | 0
ex vat
TENDER INFORMATION
| 1 | Photos of existing site
| 2 | Retail unit demise plan
3
4
LIST ANY EXCLUSIONS
1
2
3
4